## Summary Report - Mobile Testing
Test Summary Report
Test Report |  | System Test
EXECUTED | PASSED
FAILD
TOTAL TEST EXECUTED (PASSED + FAILD)
PINNDING
IN PROGRESS
BLOCKED
SUBTOTAL TEST PLANNED (PENNDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
Function | Description | % TC Executed | % TC Passed | % TC Pending | No. TC Executed | No. TC Passes | Priority
Post Module | The system should allow user to create a post ,comment on post ,like ,share the post | 100% | 91% | 0% | 11 | 11 | High
Friends Module | The system should allow users to send, accept, and reject friend requests, view and manage their friend list, search for new friends, see mutual friends, and block or unfriend other users. | 100% | 100% | 0% | 9 | 9 | High
Login Module | The system should allow users to securely log in using a valid email or phone number along with a password and provide options for logout. | 100% | 85% | 0% | 7 | 6 | High
Events Module | The system should allow users to create, edit, and manage events, invite friends, RSVP (Going, Interested, Not Going), and view the list of attendees. | 100% | 100% | 0% | 10 | 10 | High

## Summary Report - Performance Te
Test Summary Report
Test Report |  | System Test
EXECUTED | PASSED |  |  |  | 7
| FAILD |  |  |  | 0
| TOTAL TEST EXECUTED (PASSED + FAILD) |  |  |  | 7
PINNDING |  |  |  |  | 0
IN PROGRESS |  |  |  |  | 7
BLOCKED |  |  |  |  | 0
SUBTOTAL TEST PLANNED (PENNDING + IN PROGRESS + BLOCKED + TEST EXECUTED) |  |  |  |  | 7
Function | Description | % TC Executed | % TC Passed | % TC Pending | No. TC Executed | No. TC Passes | Priority
GitHub API Accessibility | The GitHub API accessibility test ensures that the base endpoint (GET https://api.github.com/) is reachable and responsive under load. | 100% | 100% | 0% | 1 | 1 | High
User Module | The User Module provides performance testing for fetching user details. It ensures that GET /users/{username} responds correctly and within acceptable response time (< 2s under load). | 100% | 100% | 0% | 1 | 1 | High
Repository Module | This module measures throughput, response time, and success rate for read and write operations. Unique repository names are used for each thread to avoid collisions. | 100% | 100% | 0% | 4 | 4 | High
Commit Module | The Commit Module tests fetching commits from a repository using GET /repos/{owner}/{repo}/commits. This ensures correct data is returned and response time remains acceptable under concurrent load. | 100% | 100% | 0% | 1 | 1 | High